NA4 Medical Imaging
CERN, November 29, 2006
Johan Montagnat

---
Agenda
10:00	Status (J. Montagnat)
10:15	Application portals (H. Benoit-Cattin)
10:45	Web interface to medical image repository (A. Fessy)
11:00	Discussion on web portals
12:30	Lunch
14:00	gLite Data Management (A. Frohner)
14:45	gLite Workfload Management System (E. Molinari)
15:30	AoB, conclusions
16:00	End of meeting

---
Milestones
MNA4.1 (PM5) HEP and Earth Sciences demonstrations
  - Completed (EGEE'06)
MNA4.2 (PM10 – Jan. 2006) Biomedical and astrophysics demonstrations
  - Coming soon – first call for candidates
MNA4.3 (PM7, PM20) User survey
  - First survey submitted (NA4 SC)
MNA4.4 (PM12, PM23) User Forum
  - User Forum II: may 2007, in conjunction with OGF in Manchester
MNA4.5 (PM18) Fusion and computational chemistery demonstrations

---
Deliverables
DNA4.1 (PM3): application deployment plan
  - completed
DNA4.2.1 (PM11 – Feb. 2006): First summary and evaluation of application usage of EGEE-II services
  - Coming soon
DNA4.2.2 (PM22): Second summary and evaluation of application usage of EGEE-II services

---
First user survey
Template distributed on Nov. 21st, returned on the 24th, submitted on the 27th...
Overall satisfaction with EGEE support mechanisms?
  - GGUS: OK for daily/local problems; difficulties to follow on longer term issues (coordination with TCG, OAG...)
  - Service deployment: difficult to get SA1 support
  - Service development: satisfying
Infrastructure
  - Using production infrastructure
  - High availability of resources
  - Stability issues reported (application-level recovery procedures needed for large scale computations)
  - Very long to get VO service deployed

---
First user survey
Middleware
  - Most used services: WMS (RB, no direct access to CEs) and DMS (File catalog, no direct access to Ses)
  - Functionality: WMS not taking into account well enough processing of short jobs; DMS limited for sensitive data management
  - Stability: WMS stability has improved but still regular job faults; GFAL-based DMS rather satisfying now
  - Performance: overall performance satisfactory except for short jobs
  - Non EGEE services: AMGA, MOTEUR, Taverna, PGRADE or application specific portals, MDM, Parrot, EncFile, Perroquet

---
TCG
Main biomed requirement: secured DMS
Little voice inside TCG
Very little resources/time to do anything with the prioritized list of requirements
Request for supporting FiReMAN/Hydra services reasonably (i.e. non development prototype) forwarded to the OAG

---
User Forum II
In conjunction with OGF, May 2007
  - Mon. 7 - Wed. 9: OGF
  - Wed. 9 - Fri. 11: EGEE User Forum II
One common day
  - Tracks on standard, business and applications
Two UF specific days
  - Parallel thematic sessions
  - Demo and posters
  - Rapporteur talks
Call for abstracts coming very soon
  - You are encouraged to participate!

---
EGEE III
Goals
  - Support
  - Community building
  - Advanced application services
Support
  - VO support – setting up VOs
  - Application porting – technical support in coordination with mdw
  - Direct user support – GGUS-like, with more operation support
Community building
  - Communities as self-reliant as possible
Advanced application services
  - Development teams coming from identified scientific disciplines

---
EGEE III
Coordination
  - NA4 steering committee
  - Co-located teams as much as possible
  - Regional coordinators (liaison with NA4 SC, reporting)
Interactions with other activities
  - Operation (SA1): through VO support team
  - Integration and testing (SA3): through development teams
  - Testing infrastructure: through VO support team
  - Dissemination (NA2)
  - Training (NA3)

---
Current medical imaging activity
No more VO-level statistics collection by JRA2
Applications
  - Production: GATE, SiMRI3D, CDSS, pharmacokinetics, gPTM3D, Bronze Standard
  - Porting: SPM for Alzheimer's, SEE++, Freesurfer for brain imaging
  - Planed: PET simulation, cardiovascular imaging
Services
  - MDM: deployment slowed down by lack of gLite services deployment
  - MOTEUR workflow manager: working on different types support
  - P-GRADE: v3 status?
  - SDJ? Web interface for medimg repository? gPTM3D file catalog?

---
Agenda
10:00	Status (J. Montagnat)
10:15	Application portals (H. Benoit-Cattin)
10:45	Web interface to medical image repository (A. Fessy)
11:00	Discussion on web portals
12:30	Lunch
14:00	gLite Data Management (A. Frohner)
14:45	gLite Workfload Management System (E. Molinari)
15:30	AoB, conclusions
16:00	End of meeting